## Product_Backlog
Id	Task	Category	Priority	Difficulty	Status	Date completed
1	Install Java 17 and MySQL Database	planning	13	1	Done
2	Read the document to define scope	planning	13	5	Done
3	Frontend structure provided	design	8	5	Done by Eduardo
4	Create Netflix website UI	design	8	5	Done by Eduardo
5	Search result page	code	5	8	done
6	Login page	code	5	5	done
7	Sign up page	code	5	8	done
8	Admin login	code	2	3	in progress
9	Authentication	code	1	8	done
10	Schema summary and tables				get reference from Eduardo
11	Create MySQL database for the project		13	1	Done
12	Create a sprintboot app [ott-platform-app]	code	1	1	Done
13	Trying to modify fake fetch code in Natflix-Frontend	code	5	5	In progress

## Sprint_1
Id	Task	Priority	Status
6	Login page	5	Done
7	Signup page	5	Done
8	Admin login	2	in progress
9	Authentication	1	Done
12	Create a sprintboot app [ott-platform-app]	1	Done

## Frontend-Modified
Id	Task	Status
6	Search icon that transform into a search bar	Done